## FSIS Re-design

## Weekly Status – November 20th, 2003

Tasks completed this week:

- Received approval from Bryce Quick on creative design of the site and flash masthead images/words.

- Completed scope document to outline 313 pages for development.

- Continue creation of CAR (Click Action Response) diagrams to identify all clickable items on each of the 300 pages defined as in scope.

- Initiated creation of the Test Approach document.

- Initiated creation of functional test scripts.

- Met with Kathy Eng of the Target Center to learn how to use screen readers for 508 Compliance Testing.  Confirmed ability to use the Target Center facilities on a regular basis during the testing effort.

- Facilitated design review meeting to present “I Want To…” options and new masthead options for the flash and default image on Wednesday, November 19.

- Identified and confirmed FSIS resources to participate in the content development effort.

- Facilitated content development session on Thursday, November 20th from 1:00 – 3:00pm.  Distributed assignments to identified content developers.

- Initiate creation of remaining 13 design templates.

- Continued to test the vRep tool with questions/answers received from Linda Eckrich.

- Continue development of HTML/ASP pages based on approved design templates.

Tasks for next week:

- Review Scope document with Sandy Facinoli and Linda Eckrich.

- Review HTML/ASP Coding Standards document with Linda Eckrich.

- Identify and schedule employees to participate in an informal Usability Test to be held in Greenbelt.

- Review updated Technical Architecture document with James Hughes and Linda Eckrich.

- Select version control and defect tracking software to be used during development and testing phases.

- Identify additional pages that will be developed by the re-design team beyond the 313 defined as in scope.  The re-design team will hire a sub contractor to develop the additional pages.

- Continue creation of remaining 13 design templates.

- Continued to test the vRep tool with questions/answers received from Linda Eckrich.

- Continue development of HTML/ASP pages based on approved design templates.

- Prepare for vRep presentation to the USDA Meat and Poultry hotline on Wednesday, December 3.

- Continue creation of CAR (Click Action Response) diagrams to identify all clickable items on each of the 300 pages defined as in scope.

- Complete Test Approach document.

- Continue creation of functional test scripts.

Issues:

- None.