## Slide 1: NIH Management Initiatives
Ms. Colleen Barros
Deputy Director for Management
Acquisition Symposium
November 10, 2004

## Slide 2: Overview
Overview of total NIH restructuring effort
Principles and Management/Governance Framework
Status report

## Slide 3: Overview – NIH Change Initiatives
Government-wide
DHHS-wide
NIH-ARAC
E-Gov
  25 known initiatives
    Largest impact is e-Travel.
    GSA announced requirement to begin installing of new system.
    DHHS has selected Gelco-based system thru Northrup Grumman.
    DHHS calling for NIH implementation in FY 2005.
A-76
  Successful NIH bids for Grants and Real Property.
  12 studies underway/completed for FY 2004.
  Preplanning for 9 studies in FY05
Accounting Initiatives
  System - all Agencies run accounting operations on single software configuration maintained by DHHS.
  Operations – Workgroups, studies exploring use of Shared Services.
Procurement Initiatives
  DHHS-wide workgroups standardizing elements of the procurement systems;
  Decisions to date include use of standard software.
  Budget – Continue decentralized services; centralize limited functions.
  Finance – Continue centralized services but within the context of a new financial system and DHHS centralization efforts.
  HR – Centralize all operations.
  Facilities – Restructure centralized functions.
  Acquisitions – Continue decentralized model but with fewer decentralized acquisitions offices.
  EEO – Centralize all operations.
  IT – Centralize selected functions
  Grants Management – Service Centers for non-IC-specific functions.

## Slide 4
Undertake administrative change that enhances the NIH research mission.
Assume ARAC report represents policy direction; implementation groups have flexibility in defining optimal approach.
Achieve efficient use of FTE’s w/o diminution of service.
Actively involve community, including customers, in implementation planning.
Create customer service advisory boards for services to be centralized.
Undertake comprehensive change management including communication and training.
Promote “best practices” through benchmarking and performance standards, and sequence efforts with IT initiatives to assure that reengineered business processes are incorporated into system development.
Achieve standard business processes.
Assure governance through Working Groups and Steering Committee.
Principles to Guide Program of Change
Coordinate, as appropriate with DHHS to maximize efficiencies.

## Slide 5: ARAC Implementation - NIH Management Framework
DDM
  Overall responsibility for the management of the program of change on behalf of NIH Director.
  Assures presentation of policy issues through the NIH Governance structure
  Assures that individual initiatives are coordinated with other NIH initiatives.
Functional Managers
  Overall responsibility for managing the development and implementation of an individual change initiative.
  Responsible for assuring that the change initiative is managed consistent with NIH/DHHS policy and the principles established by the NIH Steering Committee.
  Raise cross-cutting issues to DDM if cannot be resolved.
ARAC Implementation Groups
  Assist the Functional Manager in developing and executing the implementation plan.
  Provide advice on procedural and policy issues that emerge.
National Academy of Public Administration – Contracted by NIH to assist in the implementation of ARAC initiatives.

## Slide 6: Management/Governance Framework
NIH Working Groups
  Approve implementation plans or modifications to plans for initiatives within its purview.
  Resolve policy issues that fall exclusively within its purview.
  Make recommendations to the Steering Committee on cross-cutting or policy issues that have NIH-wide corporate consequences.
  Keep abreast of overall progress in formulating and executing the initiative and that it is consistent with NIH/DHHS policies and the principles approved by the NIH Steering Committee.
NIH Steering Committee
  Approves principles that guide NIH change initiatives.
  Provides overall oversight for the development and execution of the total program of change.
  Resolves cross-cutting or policy issues that have NIH-wide corporate consequences.

## Slide 7: NIH Governance Structure
Dr. Elias Zerhouni, Chair
Steering Committee
Ten IC Directors
Facilities
Working Group
Management
&
Budget
Working Group
Information Technology
Working Group
Intramural Activities
Working Group
Extramural Activities
Working Group

## Slide 8: Working Groups and ARAC Initiatives
Management & Budget | Information Technology | Facilities | Intramural Activities | Extramural Activities
Acquisitions | IT | Facilities |  | Grants
Finance |  |  |  | 
Budget |  |  |  | 
HR |  |  |  | 
EEO |  |  |  | 

## Slide 9: ARAC Status Report - NIH Governance
All Managers must present Implementation Plan to their Working Group and to the Steering Committee
  Purpose is to assure:
    NIH leadership agreement with Implementation Plan;
    Consistency with the principles approved by Steering Committee
    Reasonableness of proposed timelines.
  All initiatives have been presented to their respective Working Group – Acquisitions presented to the Management and Budget Working Group.
  Presentations to the Steering Committee are in progress – Acquisitions to be presented to the Steering Committee shortly.

## Slide 10: ARAC Status Report – NAPA Panel
All ARAC initiatives have been presented to a Panel convened by the National Academy of Public Administration
  Distinguished executives who oversee the NAPA staff effort.
  Primary emphasis of Panel has been to assure benchmarking, performance indicators, customer input and change management.
Acquisitions initiative presented to NAPA Panel on November 5.

## Slide 11: Status of Initiatives
EEO
  NIH-wide implementation of EEO consolidation planned for October 2004.
  Organizational structure and function definitions established.
  FTE and dollar transfers occurred Oct 3, 2004.
  Implementation plan approved and one-year transition period has begun.
  Benchmarking and best practices development underway.

## Slide 12: Status of Initiatives
IT
  FY2003 Accomplishments: have completed consolidation of 25 Help Desks to 1; 14 e-mail systems to the NIH Central System; and 21 wireless networks.
  FY2004 Initiatives completed by October 31, include:
    Establishing a single active directory to manage user identities in lieu of 18 domains--have completed 7 migrations.
    Consolidating network monitoring and problem detection/notification; remote access to the NIH Network; and network construction and management in new/renovated buildings. Network monitoring transition schedule for ICs has been developed and reconfigurations began in July.
    Restructuring videoconferencing between CIT and ORS. Consolidation objectives will be achieved with completion of Medical Visual Arts competitive sourcing.
    Restructuring lines of authority--IC CIOs to be accountable to NIH CIO for IT infrastructure. Proposed approach presented to ITWG and EOs.

## Slide 13: Status of Initiatives
Grants Management
  Consolidate training of grants management staff with coordination by the Office of Extramural Research. Two modules have been developed and approved by GMAC – will be initiated in FY 2005.
  Consolidate non-IC specific grants management functions.
    Two activities -- grants close out and NRSA appointments and terminations -- will be consolidated with the establishment of the Division of Extramural Activities Support.
    Receipt and imaging of non-competing applications centralized October 2004.
  Develop uniform core business practices to assure consistency of procedures across ICs. A set of standard award terms have been developed and will be approved by GMAC for mandatory use.
  Pilot benchmarks for determining appropriate staffing levels. Metrics for grants weight factors have been prepared, refined, and approved by GMAC. They will be applied across all ICs for comparison, and then used to formulate recommendations for next steps to take in 2005.

## Slide 14: Status of Initiatives
Human Resources
  Have undertaken a comprehensive assessment by HR customers of service needs.
  Based on assessment, have developed an HR Strategic Business Plan with 15 initiatives that focus on customers, stakeholders, internal practices, and competency development.
  Business plan was presented to MBWG in July.
  Have established a HR Strategic Advisory Committee – first meeting occurred in September.
Budget
  Workgroup has been established to:
    Identify common functions that could be consolidated centrally, and
    Strengthen the linkage between the central budget office and IC budget offices.
  An implementation plan has been developed.
  Staffing data has been collected and approaches to formalize the sharing of best practices among the budget community are being examined.

## Slide 15: Status of Initiatives
Facilities
  Functions from regional facilities at NIEHS, RML, Phoenix, and Baltimore centralized October 1, 2004.
  NIH has competed successfully as the Most Efficient Organization for real property functions but the final outcome is awaiting an independent review to identify any needed adjustments to the government’s bid.
  A plan for consolidating conference room management for rooms with capacity greater than 50 is being developed.
Finance
  An implementation group has been formed and activities currently focus on addressing issues related to the merger of the NBS and UFMS.
  NAPA is performing an organizational and business process review for determining the best organizational option for the future.

## Slide 16: Status of Initiatives
Acquisitions –
  Consolidation of NIH Acquisitions, including R&D Contracting, into 6 Service Centers.
  Project schedule drafted and being aligned with NBS deployment schedule for acquisitions.
  Alternative organizational configurations being assessed.
  Methodology being developed to determine optimal workload and staffing allocation.
  NAPA undertaking benchmarking with non-NIH Federal and University organizations.

## Slide 17: For the Future
Continue to balance all change initiatives
  Emphasis on appropriate synchronization
  Must maintain continuity in supporting the mission
Continuously evaluate
  Strengthen data analysis and oversight capability
  Customer Service Boards
  Create risk assessment capability