Comments on Transmission Line, Remote Clamp, & TL Block Review

February 26, 2002

# Overview and Status

Presenter:  N. Grossman

- (Reviewer:  J. Kilmer)  I'm concerned about the level of drafting supplied to this task. It's not clear to me that the team can keep it's schedule without more drafting help. I would encourage the Numi management to try and get some more help from the PPD/MD for this.

This has been a constant problem with the entire NuMI Project  - insufficient drafting help – resulting in much longer than anticipated time to complete drafting.  This, unfortunately, continues to be a problem.  The Project continues to work on improving this situation, or at least stopping it from getting worse.

- (Reviewer:  F. Nezrick)  I again state that I seriously question the need of the flex joint for Horn 1. Since the transverse position of Horn 1 most likely will not be scanned to verify beam centring, I do not see a justification for the flex joint. It adds extra cost, effort (time) and complexity.

The present joint allows some flexibility, albeit at a much smaller level, due to this concern.  It is no long a complicated design and allows flexibility simply by having narrower strips of aluminum and appropriate spacing of joints. (see http://www-numi.fnal.gov/numwork/tdh/tdh_index.html, Section 4.3.5).

- (Reviewer:  F. Nezrick)  In the note of Zhijing Tang of October, 2001 concerning the Finite Element Analysis of the flex joint, he notes the importance of keeping the slots at each bend to an equal length (also noted in Nancy's talk). Also if I understand the calculation correctly the slots lengths are always symmetric wrt the center of curvature for each bend of the transmission line, e.g. Figs 4, 10-14. This implies drawings on page 1, 4, 5 and 9 of the Drawing Package handout by Boettinger are incorrect.

The horn joint designs have been changed and no longer include slits.  (see http://www-numi.fnal.gov/numwork/tdh/tdh_index.html, Section 4.3.5)

- (Reviewer:  F. Nezrick)  It is planned that the prototype flex joint and remote clamp will be pulse tested at MI8. It is essential that the prototype survive the testing. However we should require more. The testing plan lacks quantitative measurements (deflection at specific points, resonant frequencies, etc.) which might demonstrate agreement with expectations (ANSYS calculations, etc.) thus supporting an anticipated longevity.

Testing at MI8 has included some measurements of vibration & deflection.  This information has not yet been summarized and compared to ANSYS.

- (Reviewer:  F. Nezrick)  The transmission lines in the target hall when pulsed will act like xylophone bars; they will undergo transverse and longitudinal vibrations. There is probably time and space to develop appropriate dampening methods after the TL system is installed. However, vibrations from the transmission lines and flex joints in and under the horn module should be better understood soon so space, e.g. for dampers, might be allowed in the module design. Hints might be obtained during the flex joint testing program at MI8.

The joints tested at MI8 are the ones that will go in the Target Hall.  The spacing of the clamps at MI8 is quite similar to the Target Hall spacing.  Measurements of deflection and vibration have been made at MI8 and as a result we are not concerned.  These results need to be written up.

- (Reviewer:  F. Nezrick)  Nancy listed on Pg. 21 of her handout a Concern ::: "Schedule is a bit tight." In the part of the installation schedule not shown on Pg. 20, but discussed at the review, it appeared that the amount of time allowed for testing (pulsing) the horn system in its running position was about one month. If no failures or major modifications are encountered, a month may be sufficient. My concern is that for various reasons this testing time might be reduced even more. It should be remembered this will be the first time the horn system will be operated in this configuration (supported from actual module with all appropriate motion controls and monitors installed, target installed, target hall transmission line attached, etc., etc.). Proper testing time must be rigidly scheduled, even if only 3rd shift.

We will do the best we can in this area.

- (Reviewer:  D. Pushka)  Resources are just barely enough to pull off this work. Key areas where more help could be efficiently used is for drafting and will eventually include technicians for stripline assembly. Project management for NuMI needs to bring to the attention of the Beams Division management and relevent department heads the presently forseen technican shortage during the Miniboone installation and the NuMI work so that they can react in sufficient time to borrow additional help from other areas of the laboratory.

We have done and will continue to do the best we can in this area.

- (Reviewer:  D. Pushka)  While the following comment is outside the presently budgeted scope of work and will require a large effort to pull off, the full production stripline and powersupply and horns one and two should be assembled in MI 8 after Miniboone clears out as a full scale assembly test. The full system will need to be assembled eventually. Current plan is to assemble it underground and this work is likely to be on the critical path (or near enought to it the any problems in the stripline assembly will put CD-4 in jeopardy). By starting the assembly earlier and in a service building, problems can be solved without affecting the critical path. This is more work because some effort will need to be duplicated, but if we are serious about reducing the length of the technical component installation, this is a wise and prudent addition.

We will do some level of assembly at MI-8 – whatever seems to make sense given the time and resources.