| ASR-11 PROGRAM FAA-UNIQUE CDRL ITEMS AND CONTRACT LETTERS # FAA REPLIES DUE TO RAYTHEON AS OF 22 JAN 08 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ### Letter No. | ### Title | CDRL No. | ### Reply Due to Raytheon | ### Point(s) of Contact | Notes |
| R07-0198 | ### Request for Release of Holdback – AGS, YNG, MOB, MYR |  | ### 7 May 07 | ### C. Cole | PENDING – Letter E08-0005 sent to ESC on 10 Jan 08. |
| R07-0232 | ### As-Built Drawings for Little Rock, AR | ### A026-LIT-1 | ### 29 Jun 07 | ### S. Jarvis | OVERDUE – Raytheon will send a new set of drawings to ASW to replace missing copies (e- mail 25 Sep 07). |
| R07-0249 | ### Request for Release of Holdback – LIT, MOB, MBS |  | ### 29 Jun 07 | ### C. Cole | OVERDUE – Raytheon states all action items are closed and requests release of holdback funds. |
| R07-0349 | ### As-Built Drawings for North Valley, AZ | ### A026-SDL-1 | ### 4 Sep 07 | ### I. Coleman | PENDING – Approval letter E08-0006 sent to ESC on 10 Jan 08. |
| R07-0399 | ### Updated As-Built Drawings for Youngstown, OH | ### A026-YNG-2 | ### 30 Oct 07 | ### S. Jarvis | OVERDUE – |
| F-FAASS-07-0040 | ### SATP for Panamint Valley, CA - Update | ### A009-QPM-3 | ### 14 Nov 07 | ### M. Meir | ON HOLD – This submittal does not reflect current configuration. Another update is required once the final configuration is decided. |
| R07-0449 | ### Request for Release of Holdback – Champaign, IL |  | ### 19 Nov 07 | ### C. Cole | OVERDUE – Raytheon states all action items are closed and requests release of holdback funds. |
| R07-0441 | ### SATP for Sioux City, IA – Updated Final | ### A012-SUX-4 | ### 26 Nov 07 | ### C. Brookshire | PENDING – Approval letter E08-0010 sent to ESC on 15 Jan 08. |
| R07-0442 | ### SATP for Midland, TX - Final | ### A012-MAF-2 | ### 30 Nov 07 | ### C. Brookshire | PENDING – Approval letter E08-0011 sent to ESC on 15 Jan 08. |
| R07-0444 | ### SATP for Kahului (Maui), HI – Updated Final | ### A012-OGG-7 | ### 3 Dec 07 | ### C. Brookshire | OVERDUE – |
| R07-0460 | ### Request for Release of Holdback – Reading, PA and North Valley, AZ |  | ### 5 Dec 07 | ### C. Cole | OVERDUE – Raytheon states all action items are closed and requests release of holdback funds. |
| R07-0469 | ### SAT Report for Velvet Peak, CA | ### A024-QVP-2 | ### 4 Jan 08 | ### M. Nostheide | OVERDUE – |
| R-FAASS-07-0043 | ### Legal Description for Melbourne, FL – Revised | ### A005-MLB-LD-5 | ### 7 Jan 08 | ### C. Leid | OVERDUE – |
| R07-0483 | ### As-Built Drawings for Velvet Peak, CA | ### A026-QVP-2 | ### 8 Jan 08 | ### I. Coleman | PENDING – Approval letter E08-0007 sent to ESC on 10 Jan 08. |
| R-FAASS-07-0044 R-FAASS-07-0035 | ### SATP for Wilkes Barre, PA – 2 Updates | ### A009-AVP-3 A009-AVP-4 | ### 16 Oct 07 14 Jan 08 | ### C. Brookshire | OVERDUE – |
| R07-0531 | ### Response to Comments – SAT Report for Fargo, ND | ### A024-FAR-3 | ### 21 Jan 08 | ### M. Nostheide | OVERDUE – Approval due to Raytheon. |
| R-FAASS-07-0018 R-FAASS-07-0045 R-FAASS-07-0048 | ### SATP for Corpus Christi, TX – Final and Update | ### A009-CRP-2 A009-CRP-3 A009-CRP-4 | ### 26 Apr 07 8 Jan 08 21 Jan 08 | ### C. Brookshire | OVERDUE – |
| R07-0532 | ### Response to Comments – SAT Report for Lexington, KY | ### A024-LEX-2 | ### 21 Jan 08 | ### M. Nostheide | OVERDUE – |
| R07-0533 | ### Response to Comments – SAT Report for Midland, TX | ### A024-MAF-2 | ### 21 Jan 08 | ### M. Nostheide | OVERDUE – |
| R07-0534 | ### Response to Comments – SAT Report for North Valley, AZ | ### A024-SDL-2 | ### 21 Jan 08 | ### M. Nostheide | OVERDUE – |
| R07-0500 | ### As-Built Drawings for Springfield, IL - Preliminary | ### A026-SPI-1 | ### 28 Jan 08 | ### S. Jarvis | PENDING – Approval letter E08-0009 sent to ESC on 10 Jan 08. |
| R07-0504 | ### As-Built Drawings for Colorado Springs, CO - Final | ### A026-COS-2 | ### 28 Jan 08 | ### I. Coleman | PENDING – Comment letter E08-0004 sent to ESC on 10 Jan 08. |
| R07-0507 | ### SAT Report for Springfield, IL | ### A024-SPI-2 | ### 30 Jan 08 | ### M. Nostheide | Comments due to Mike Nostheide by 16 Jan 08. Contract letter due to Bob Kessler by 23 Jan 08. |
| R07-0514 | ### As-Built Drawings for Panamint Valley, CA | ### A026-QPM-1 | ### 4 Feb 08 | ### I. Coleman | Comments due to Isaac Coleman by 18 Jan 08. E-mail authorization due to Bob Kessler by 25 Jan 08. |
| R08-0006 | ### SAT Report for Panamint Valley, CA | ### A024-QPM-2 | ### 25 Feb 08 | ### M. Nostheide | Comments due to Mike Nostheide by 11 Feb 08. Contract letter due to Bob Kessler by 18 Feb 08. |
| R08-0018 | ### As-Built Drawings for Reading, PA - Final | ### A026-RDG-2 | ### 28 Feb 08 | ### C. Leid | Comments due to Cassandra Leid by 14 Feb 08. E-mail authorization due to Bob Kessler by 21 Feb 08. |

| # ASR-11 PROGRAM FAA-UNIQUE CDRL ITEMS AND CONTRACT LETTERS # RAYTHEON REPLIES DUE TO THE FAA AS OF 22 JAN 08 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ### Letter No. | Title | CDRL No. | Reply Due from Raytheon | Point(s) of Contact | Notes |
| ### E07-0187 | ### SAT Report for Reading, PA | A024-RDG-2 | ### 19 Dec 07 | ### M. Nostheide | OVERDUE – Raytheon to submit change pages. |
| ### E07-0203 | ### SAT Report for Sioux City, IA | A024-SUX-2 | ### 12 Jan 08 | ### M. Nostheide | OVERDUE – Raytheon to submit change pages. |
| ### E07-0207 | ### As-Built Drawings for Pueblo, CO – Update to Final | A026-PUB-3 | ### 8 Feb 08 | ### I. Coleman | Raytheon to submit updated drawings. |
| ### F08-0003 | ### SATP for Melbourne, FL – 3rd Final | A009-MLB-4 | ### 22 Feb 08 | ### C. Brookshire | Raytheon to submit the RFI Mitigation Analysis Report |

Note:  Information added since the last report, and other important highlights, is shown in bold type.		        Prepared by: Bob Kessler, AT0-T-ASR11, 202-385-8743